## Dublin Bikes Agile Project
At Risk | Sprint | Issue | Status | Feature Type | Story Points | Start | Finish | Duration | Assigned To | Issue Key | Comments | Predecessors
Learn how to use this template
|  | AGILE PROJECT |  |  |  | 2017-03-13 | 2017-04-22 | 41d
|  | Sprints |  |  |  | 2017-03-11 | 2017-03-24 | 14d
|  | Sprint 1 |  |  |  | 2017-03-11 | 2017-03-22 | 12d
| Sprint 1 | Feature 1: User Stories and site design | Not Started | Web Design |  | 2017-03-11 | 2017-03-22 | 12d | All
Feature 2: Project Management
|  | Task 1: XXXXX Cara- Templates, update tasks, Etc. | Started
|  | Task 2: Research GitHub and create repositories | Completed |  |  | 2017-03-11 | 2017-03-13 | 2hr | Darragh
|  | Task 3: Create Github tutorial guide. | Completed |  |  | 2017-03-13 | 2017-03-13 | 2hr | Darragh
|  | Task 4: Setup skeleton project | Not Started |  |  | 2017-03-14 | 2017-03-25 | 2hr | Darragh |  | Feedback to be provided on skeleton to finish.
|  | Feature 2: Flask Implementation | Not Started | Data Analysis |  | 2017-03-11 | 2017-03-24 | 14d
|  | Task 1: Research how to implement Flask | Not Started |  |  | 2017-03-13 | 2017-03-21 | 4hr | All
|  | Task 2: create simple web page | Not Started |  |  | 2017-03-11 | 2017-03-24 | 14d | Tao
|  | Task 3: parse in static data | Not Started |  |  | 2017-03-11 | 2017-03-24 | 14d | Darragh
|  | Task 4: set design blueprint for site layout & data display | Not Started |  |  | 2017-03-11 | 2017-03-24 | 14d
|  | Task 5: Create Flask tutorial guide. | Not Started | [5 empty] | Tao
|  | Feature 3: Establish database | Not Started | DB/Data Collection |  | 2017-03-11 | 2017-03-24 | 14d
|  | Task: 1 Research how to parse json to sql using python | Started |  |  | 2017-03-13 | 2017-03-14 | 2hr | Darragh
|  | Task: 2 Parse static data into sql database | Not Started |  |  | 2017-03-14 | 2017-03-15 | 4hr | Darragh
|  | Task: 3 design DB structure | Not Started |  |  | 2017-03-15 | 2017-03-15 | 2hr | Darragh
|  | Task: 4 write algor to create SQL DB (dynamic & static) | Not Started |  |  | 2017-03-20 | 2017-03-24 | 3hr | Darragh
|  | Task 5: Create json to sql guide | Not Started |  |  | 2017-03-20 | 2017-03-24 | 2hr | Darragh
|  | Sprint 2 |  |  |  | 2017-03-27 | 2017-04-09 | 14d
| Sprint 2 | Feature 4: Site API | Not Started | Web Design |  | 2017-03-27 | 2017-04-09 | 14d
|  | Task 1: Google Maps API |  | Web Scraper/API |  | 2017-03-27 | 2017-04-09 | 14d
|  | Task 2: Weather API |  | Web Scraper/API |  | 2017-03-27 | 2017-04-09 | 14d
|  | Feature 5: Run Web Scrapper | Not Started | Web Scraper/API |  | 2017-03-27 | 2017-04-09 | 14d
|  | Task 1: Set up on EC2 | Not Started | Web Scraper/API |  | 2017-03-27 | 2017-04-09 | 14d
|  | Task 2: Reformat, fix bugs | Not Started | Web Scraper/API |  | 2017-03-27 | 2017-04-09 | 14d
|  | Sprint 3 |  |  |  | 2017-04-10 | 2017-04-22 | 13d
| Sprint 3 | Feature 7 | Not Started |  |  | 2017-04-10 | 2017-04-22 | 13d
Backlog
| Backlog | Feature 10 | Not Started
TRUE | Backlog | Feature 12 | Not Started